## Slide 1
INTEGRATING DIVERSITY IN SOCIAL DIALOGUE
Strengthening the EU’s Labour Market in the Digital and Green Age
Kick-off meeting 30 April 2025
20 September, 2024
Funded by Horizon Europe Project No. 101177913
Lessons for policy and practice – signs of innovative strategies?
WP6, Marta Kahancová

## Slide 2
WP6: Lessons for policy and practice – signs of innovative strategies?
Synthesize and systematize knowledge produced in WPs 2-5 to formulate policy implications aligned with the framework in WP1
Verify and test policy implications with stakeholders through peer-learning dialogue events
Develop new strategies for adjusting SD structures to integrate the needs of NSWs, taking into account specific challenges
Create an Open Policy Toolbox with instruments to enable better integration of NSWs

## Slide 3
T6.1 (M12-48)
T6.2 (M25-40)
T6.3 (M25-48)
Analysis and preparation of a policy resource paper based on WP2-5 findings
Peer-learning dialogue organisation
Open Policy Toolbox - 12 policy briefs, each devoted to a specific policy measure emerging from T6.1 and T6.2
WP6: Tasks and deliverables
Policy report - based on a summary analysis of findings and policy recommendations emerging at the PLDs (M45)
Policy toolbox - comprehensive guide for policy makers (M48)
Policy briefs - advise for stakeholders (12 briefs, each on one measure?) (M42)

## Slide 4
Deliverable: Peer-learning dialogue events
Aim: bring together stakeholders acting on behalf of NSW and let them interact, exchange ideas, provide peer feedback, and learn from each other
Agenda:
  presenting research findings and policy recommendations
  selected stakeholders present their approaches, strategies, and comment on the research findings
  moderated discussion, leading to a common understanding of which policies work (in which business models, for which types of NSW, for which types of actors,...)

## Slide 5
Deliverable: Policy learning resource paper
Structured document to provide practitioners/stakeholders information, insights, and guidance on a specific topic.
  Informative and clearly structured: Clear explanations, definitions, contextual background
  Evidence-based: Includes research findings and expert opinions to support the content (how to represent/embrace the interests of NSW)
  Engaging and accessible: Written in a way that is easy to understand, often including visuals, charts, or examples to enhance comprehension
  Application-oriented: Can contain best practices, country-specific examples in boxes or practical applications to reinforce learning.

## Slide 6
Deliverable: Open Policy Toolbox
Identify 12 policy measures based on research and the PLDs, write 1 policy brief on each measure
Compile the measures into a policy toolbox - selection of measures matters! Translations?
Use for dissemination purposes - close interaction with WP7

## Slide 7
WP6: Interactions
Internal: WP2-5, legal frameworks for policy actors, NSW as core vs. NSW as periphery, sectoral/occupation focus
External - national stakeholders (identify in each IR scheme and business model, focus below peak-level social partners, focus on sectoral/occupational representation)
External - EU-level and international policy makers and social partners, e.g., ILO, GLO, ELA, EC, OECD, ETUC, BusinessEurope etc. (interaction with policy makers and stakeholders, strategies and action plans)

## Slide 8
Thank you for your attention!

## Slide 9
  Assoc.Prof. in Public Policy
  Industrial relations and NSW expertise
  Research focus on CEE
  Expert support for EC (Employment Policy) and ELA (Tackling undeclared work), EU-level unions (strengthening SD and bargaining)
Marta Kahancová
Adam Šumichrast
Martin Kahanec
Simona Brunnerová
Competence: team@celsi
INTEGRATE
DIALOGUE
  Prof. of Public Policy CEU Vienna
  Expert on migration and ethnicity in the labour market
  Vice-president Academia Europea and Head of Economic, Business and Management at Academia Europea
  Econ.advisor to the EC
  PhD. in labour history
  Expertise in research on unions, social dialogue, bargaining, NSW
  Horizon projects TransEuroWorks, EGRUiEN
  Third-country nationals in platform work
  Policy work for Eurofound and EFFAT
  MA in Public Policy
  Research on migrants’ interest representation (agency workers, care workers)
  Research on smart bargaining strategies (with UNI Europa) and innovative technologies for policy (PICUM)