## Slide 1: Personal and household services in Central and Eastern European Countries: Improving working conditions and services through industrial relations PERHOUSE
Monthly meeting 28 June, 2023, online
The project is funded by the European Union; Ref. 101052340

## Slide 2: Agenda
Reporting (Sona Mikulíková, CELSI) State of art - surveys (discussion, troubleshooting) State of art - interviews (discussion and troubleshooting) D2.1. and D2.2. - next steps AOB

## Slide 3: Demand survey – number of responses
ANSWER CHOICES | RESPONSES | 
Bulgaria | 1.02% | 3
Croatia | 1.70% | 5
Czechia | 3.40% | 10
Estonia | 14.29% | 42
Hungary | 5.78% | 17
Latvia | 1.36% | 4
Lithuania | 0% | 0
North Macedonia | 22.11% | 65
Poland | 17.69% | 52
Romania | 5.10% | 15
Slovakia | 14.97% | 44
Slovenia | 10.54% | 31
Other | 2.04% | 6
TOTAL |  | 294

## Slide 4: Demand survey – few preliminary results
1g. Please sum up if you did or did not purchase any personal or household services in the last 5 years.
Answered: 242 Skipped: 52
ANSWER CHOICES | RESPONSES | 
Yes, at least one from the list above | 78.51% | 190
No, no services | 21.49% | 52
TOTAL |  | 242

## Slide 5
2. If you marked more than one service in the previous questions, please choose the most frequent type of service you purchased. Please mark only one type of service.
Answered: 173 Skipped: 121
Chart: 
| Care for a child | Care for a dependent adult | Housekeeping (cleaning, laundry, shopping, cooking) | Small repairs | Gardening | Care for pets/animals | Other (please specify)
 | 0.1387 | 0.0925 | 0.3006 | 0.3468 | 0.0231 | 0.0462 | 0.052

## Slide 6: 5.1. What is your age?
Answered: 193 Skipped: 101
Chart: 
| Under 20 | 21 - 30 | 31 - 40 | 41 - 50 | 51 - 60 | 61 - 70 | Over 70
 | 0.0052 | 0.1244 | 0.2902 | 0.3886 | 0.1295 | 0.0363 | 0.0259

## Slide 7: 5.2. What is your sex/gender?
Answered: 192 Skipped: 102
Chart: 
| Female | Male | Other | Do not want to respond
 | 0.7292 | 0.2344 | 0.0156 | 0.0208

## Slide 8: 5.9. Which best describes where you live?
Answered: 190 Skipped: 104
ANSWER CHOICES | RESPONSES | 
A big city (more than 100 000 inhabitants) | 56.84% | 108
The suburb or outskirts of a big city | 7.89% | 15
A town or a small city (less than 100 000 inhabitants) | 22.63% | 43
A country village (up to 2000 inhabitants) | 11.58% | 22
A farm or home in the countryside | 1.05% | 2
TOTAL |  | 190

## Slide 9: 3.2. There might be also other reasons why you did not purchase any personal and household services. Please rate each of the following reasons on a 5-point scale.
Answered: 41 Skipped: 253
Chart: 
| There are sufficient public services outside the household available - no services in the household are needed | I cannot afford any such services | I have looked for some services but could not find any | It is too complicated to use personal and household services or hire somebody
Strongly disagree | 0.0769 | 0.0513 | 0.4103 | 0.1622
Disagree | 0.1795 | 0.2051 | 0.2821 | 0.1892
Neither disagree nor agree | 0.4103 | 0.2821 | 0.2308 | 0.4324
Agree | 0.2051 | 0.2821 | 0.0769 | 0.1622
Strongly agree | 0.1282 | 0.1795 | 0 | 0.0541

## Slide 10: Social dialogue survey – state of art

## Slide 11: Interviews with national stakeholders
Methodological note and interview topics
  Exploring the engagement in social/civil dialogue in the PHS
  Identification and addressing the challenges in PHS by social actors
  The interrelation to the EU-level social partners and policies in PHS
  21 – 23 Q
Draft commented – comments addressed – finalised
Supporting letter and informed consent (adjust)
Translations (?)
Contact database
First experiences?

## Slide 12: Interviews with national stakeholders – first experiences
Some of the partners already managed first interviews
The interview guide is too structured – some of the wording is too complicated - partners can adjust and simplify, use it only as a guide, change the order of the questions/topics, but keep the structure of the summary
Respondents have a tendency to focus on their personal experiences fist – give them floor, but have in mind that we look for the organisation’s attitudes and standpoint
The personal experiences can be used as an additional findings/stories similar to the focus groups
In the summary (max. 1 page/interview) – for each of the 3 topics, only the most relevant findings to be included, 1 – 2 paragraphs for the purpose of the comparative report

## Slide 13
ACTIVITY | MONTHS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | M 1 | M2 | M 3 | M 4 | M 5 | M 6 | M 7 | M 8 | M 9 | M 10 | M 11 | M 12 | M 13 | M 14 | M 15 | M 16 | M 17 | M 18 | M 19 | M 20 | M 21 | M 22 | M 23 | M 24
 | 08/22 | 09/22 | 10/22 | 11/22 | 12/22 | 01/23 | 02/23 | 03/23 | 04/23 | 05/23 | 06/23 | 07/23 | 08/23 | 09/23 | 10/23 | 11/23 | 12/23 | 01/24 | 02/24 | 03/24 | 04/24 | 05/24 | 06/24 | 07/24
WP1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A1.1 Management and communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A1.2 Kick-off meeting (Slovakia) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A1.3 Interim project meeting (online) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A1.4 Online progress meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A1.5 Quality control and reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A2.1 Literature review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A2.2 Comparative data evidence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A2.3 Conceptual and analytical framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A3.1 EU level interviews |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A3.2 Online demand survey |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A3.3 Online survey among PHS stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A4.1 Preparation of case studies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A4.2 Preparation of national policy briefs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A4.3 Focus groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A5.1 Comparative report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A5.2 Comparative policy brief |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6.1 Project website |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6.2 National policy workshops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6.3 Final conference |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6.4 Documentaries – national results |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6.5 Documentary – comparative results |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6.6 Country leaflets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 14
Work packages and deliverables III.
 |  | DUE DATE | 
 | NAME OF THE DELIVERABLE | Project month | Calendar month
WP1: | Project management and coordination |  | 
 | D1.1. Kick-off meeting (Bratislava, Slovakia) | M1 (M3) | 10/22
 | D.1.2.Interim meeting (online) | M10 | 5/23
 | D1.3. Feedback questionnaire | M24 | 7/24
 | D.1.4. Reports to the European Commission - CELSI | M12, M24 | 7/23, 7/24
WP2: | Analytical framework |  | 
 | D2.1. Working paper on conceptualization of PHS sector in CEE due to 7/23 | M6 | 1/23
 | D2.2. Metholodogical tools (survey, interviews, focus groups, outlines) due to 7/23 | M6 | 1/23
WP3 | Stakeholders views |  | 
 | D3.1 EU Stakeholder views study | M18 | 1/24
 | D3.2. Policy brief on stakeholder views | M18 | 1/24
WP4 | National case studies |  | 
 | D4.1 National case studies in 6 CEE countries | M18 | 1/24
 | D4.2 Policy briefs in 6 CEE countries | M18 | 1/24
WP5 | Comparative report |  | 
 | D5.1 Comparative report | M20 | 3/24
 | D5.2 Comparative policy brief | M20 | 3/24
WP6 | Dissemination |  | 
 | D6.1 Project website | M24 | 7/24
 | D6.2 National policy workshops (6 countries) | M16 | 11/23
 | D6.3 Final online conference | M23 | 6/24
 | D6.4 Interactive video documentaries (6 countries, 1 comparative) | M23 | 6/24
 | D6.5 Country leaflets on PHS sector (in national language and EN; for 6 countries) | M17 | 12/23
DELIVERABLES AND DEADLINES

## Slide 15: Deliverables due to 7/2023
Project No. 101052340
D2.1. Working paper on conceptualization of PHS sector in CEE
The paper is based on the literature review and will encompass all the main findings and
set the PHS sector's central concept and future analysis. The aim of the working paper is to provide
a comprehensive framework of the upcoming research activities of the consortium.
The format is electronic, English language).
D2.2. Methodological tools (survey, interviews, focus groups, outlines)
This deliverable contains all data collection tools for the tasks in WP3 and WP4:
Questionnaire for demand survey + dissemination strategy
Questionnare on social partners + dissemination strategy
Interview guide for EU-level stakeholders (CUNI)
Interview national-level stakeholders guide
Outline of the national case studies.
Three focus groups scripts for PHS workers (child care, adult care, non-care)

## Slide 16: Future steps - thinking ahead (timeline, deadlines, etc.)
Project No. 101052340
National cases – national reports
D4.1 National case studies in 6 CEE countries + translation into 6 languages: due to M18/JAN24 max 30 pages max + annexes
D4.2 Policy briefs in 6 CEE countries in six languages M18/JAN24 (4 pages - CELSI template)
First drafts of the national reports + briefs – deadline END OF OCT 2023
D6.2 National workshops in 6 countries due to 11/2023 (at the beginning of NOV)
The workshops aim to discuss and disseminate the findings.
The workshops will be held in 6 languages: Polish, Czech, Slovak, Slovenian, Macedonian, Estonian in the partners' countries.
It will be one-day workshops per 20 participants.
The national partners wil provide invitations, agenda, presence list.

## Slide 17: Next steps – to discus
Both online surveys will be continuing during July and August
Focus groups, outline, D2.1 - to be soon on drive – comments/feedback, finalising
Mind the timeline
Meeting in July – scheduled upon need (request the coordinator)
August - early second week due to reporting (once the EC portal will be opened) – doodle will be provided to all.

## Slide 18
Have a nice summer!