## Slide 1
@CEPS_thinktank
Negotiating return to work in the age of demographic change through industrial relations (REWIR)
(with support from the European Commission Grant Agreement VS/2019/0075)
Manon Jacquot
31st January 2020
Rome, Italy

## Slide 2
Project management and next steps

## Slide 3: Next steps – administrative (1)
Reporting:
  Technical and financial interim reports for REWIR
  The interim reporting is prepared and being submitted to the EC together with the mid-term financial reporting, request for pre-financing and first deliverable of the project (analytical and conceptual framework)
  Internal Deadline 28 February 2020
EC has 60 days to approve: 30 April 2020
CEPS will pay 40% of the total amount:

## Slide 4: Next steps – administrative (2)
Meeting with the project officer
  Emphasis on communication and dissemination activities
  Feeding the project website regularly is important
Next (and last) project meeting date to be decided
  (Early) July in Sibiu? Doodle
Final conference in Brussels
  Deciding on the date ASAP – EC is interested in participating, but they need to know the details in advance

## Slide 5: Next steps – research activities (1)
WP2: Stakeholders’ views
Deliverables: June 2020
  D2.1:Working paper on EU-level social partners’ views and involvement in return to work policies, evaluating the potential of EU-level industrial relations for designing return to work (M16) (CEPS)
  D2.2: Working paper presenting benchmark case studies on France, Germany and the UK, their return to work policies and best practices, lessons for other countries and EU-level policy making (M16) (Amir)

## Slide 6: Next steps – research activities (2)
WP3: Company level perspective
Deliverables: due June 2020
  D3.1:6 national reports, addressing the role of company-level industrial relations in facilitating return to work and identifying best practices, based on the group discussions and surveys (M16) (All partners)
  D3.2: 6 national policy briefs summarising country findings using national and company-level evidence (English and main national language of country) (M16) (All partners) template is available

## Slide 7: Next steps – research activities (3)
WP4: comparative research
  Drafting comparative report and policy brief (CEPS with contributions from all partners)
    Deliverable: Comparative report – October 2020
    Comparative policy brief – October 2020
  Policy recommendations (CEPS, with inputs from all partners)
    Report presenting policy recommendations on of current and future roles of industrial relations as a prominent channel to encourage longer labour market involvement in the context of demographic change – October 2020

## Slide 8: Next steps – research activities (4)
WP5: dissemination and communication
  Website:
    Continue populating the website content (minutes of meeting and publications)
  Webinar: all partners (until February 2021)
    Series of videos with topics to be discussed in Sibiu
  Final conference – February 2021 preferably end of January
    Decide on a date, agenda etc. early enough to start advertising in advance
  Publications
    Publish research on project website
    Submit to academic journals – internal discussion on interests

## Slide 9
1 Place du Congres, 1000 Brussels
Tel: (+32 2)229 39 11
info@ceps.eu
Thank you!
@CEPS_ThinkTank